| Event: Christchurch Earthquake |  | Section/Function/agency: Science Liaison Team |
| --- | --- | --- |
| Date: 07/03/2011 | Time: 1200 |  |
| Operational Period: |  | Originator Record #: 010 |

- Current situation (incidents, action taken, resource status, personnel numbers etc)

- Geospatial:

- - High resolution aerial photos flown on 24 February are being used for systematic photo interpretation mapping of landslide, rockfall and other slope-related ground damage, as well as liquefaction and landslide field work.

- - Planning for the LiDAR acquisition flight continues.

Earthquake Activity & Deformation:

- Aftershocks continue to decrease in frequency, though some remain sizeable. Appendix A illustrates the magnitude and frequency of aftershocks from 22 February to 7 March 2011.

- An earthquake science factsheet is now available for community briefings and will also be available on the www.canterburyearthquake.govt.nz website.

- Landslides:

- Teams of geotechnical engineers continue to prioritise more detailed assessments for evacuated areas.

- Continuous GPS monitoring continues on Kinsey Terrace, Glendavere and Balmoral Terrace.

- One rockfall was reported in Heberden Ave, Sumner, yesterday Sunday 6 March.  This area is currently evacuated.

- Grant Dellow from USAR has written an evacuation/red placard reconciliation plan for the Port Hills that will be implemented over the coming week.  The purpose of the plan is to systematically work through areas that have been evacuated to reassess the threat to homes and to make sure that as few people are out of their homes as possible, and that homes that continue to be evacuated are red stickered, to reduce confusion.  The plan has been signed off by Director Ops, Building evaluation, Police, Fire, the Geotechnical Steering Group and the National Controller.

- A process for ongoing assessment and remediation of evacuated areas is being developed at present by Christchurch City Council.

- Geotechnical assessment teams continue to assess high risk areas on the hills, and contractors from Geovert are moving their remedial operations to removing rocks along the Wakefield Ave/Heberden Ave areas of Sumner.

- Helen Grant and Mark Yetton of the Geotechnical Steering Group attended two community briefings yesterday at Waltham Park and Somerfield Park. There was a lot of interest in the geotechnical issues from hill suburb residents.  We have undertaken to develop a geotechnical factsheet to explain the physical processes and the where to from here.  We will attend three more community briefings today - McCormacks Bay, Sumner and Lyttelton.

- Liquefaction:

- - University of Canterbury have completed a draft liquefaction map based on the previous 11 days of reconnaissance work.

- - Both the Japanese and USA GEER teams have now returned home.

- Outstanding Issues / Challenges / Problems:

- Anticipated Priorities / Activities: (For future operational periods)

- Landslides:

- Reconnaissance inspections continue, providing advice to USAR teams on landslide related ground damage, including where requested, survey data relating to ground stability.

- Development of the landslide geodatabase and associated maps will continue.

- Liquefaction: Addition of the CBD area to the draft liquefaction map being prepared by University of Canterbury.

APPENDIX A:

Magnitude and frequency of aftershocks from 22 February to 7 March 2011.